## Sheet1
DEVELOPMENT LOG
Project Name IAC Onboarding Process
Project Id ------------------
Project Manager Harshada Topale
Project Sponsor Harshada Topale
SL NO ACTIVITY DESCRIPTION CHALLENGES ENCOUNTERED DECISIONS MADE PROGRESS UPDATE NEXT STEPS DEPENDENCIES
1. Started working on onboarding workflow automation None Decided to use Java for workflow automation. Completed initial script for user registration Plan testing and debugging of registration process. None
2. Encountered issues with API integration API endpoints were not well-documented None Successfully integrated user document submission Start working on approval process automation. Dependency D1
3. Resolved API integration issues None None Completed approval workflow automation. Completed approval workflow automation. Dependency D1
4. Began performance testing of onboarding dashboards None Decided to optimize database queries for dashboards Identified slow-loading dashboards Optimize database queries for dashboards. Dependency D2
5. Improved dashboard performance None None Dashboard now load faster. Continue performance testing and optimization. Dependency D2
6. Completed development phase None None All development tasks for onboarding and dashboards Prepare for project review and testing. None