## Sheet1
LESSONS LEARNT LOG
Project Name IAC Onboarding Process
Project Id ----------------------
Project Manager Harshada Topale
Project Sponsor Harshada Topale
SL NO DATE RAISED EVENT LESSON CATEGORY EARLY WARNING SIGNS RECOMMENDATIONS ACTIONS OWNER STATUS COMMENTS
1. 10-08-2023 Integration Challenges Technical YES Conduct thorough integration assessments early in project planning Resolved Swetha Closed Successfully mitigated; no impact on project timeline
2. 15-08-2023 Communication Issues Communication YES Communicate project progress transparently. Implemented Swetha Closed Improved communication
3. 22-08-2023 Performance Testing Challenges Testing YES Include performance testing from project initiation. In Progress Swetha Ongoing Performance enhancements in progress
4. 10-09-2023 Traceability Matrix Oversight Project Management YES Develop and maintain a traceability matrix from project inception. Implemented Swetha Closed Improved project tracking and requirement management.
5. 20-09-2023 Risk and Dependency Management Project Management YES Continuously assess and update risk and dependency registers Implemented Swetha Closed Risks managed effectively, no major project disruptions.