## Sheet1
TEST PLAN
Project Name IAC OnBoarding Process
Project Id ------------------------------
Intern Name Revuru Sree Swetha
Project Manager Harshada Topale
INTRODUCTION
This test plan outlines the testing approach for automating onboarding workflows and evaluating the performance of the associated dashboards.
The project's goal is to streamline onboarding processes and ensure efficient and responsive dashboards.
The goal is to ensure that the applcation functions correctly, meets user expectations, and is free of critical defects.
SCOPE
Automation of onboarding workflows, including user registration, document submission, and approval processes.
Performance testing of dashboards related to onboarding to ensure responsiveness and data accuracy.
QUALITY OBJECTIVE
Validate the functionality of automated onboarding workflows.
Identify and report defects in the onboarding automation.
Assess the performance of dashboards during peak usage.
Ensure data accuracy and real-time updates on dashboards.
TEST DELIVERABLES
Test cases for onboarding workflows.
Performance test scripts.
Test reports, including defect reports and performance metrics.
TEST ENVIRONMENT
Onboarding system environment similar to production.
Dashboards accessed on representative hardware and network configurations.
Load testing tools (e.g., JMeter) for performance testing.
TEST PLAN
ITEMS TO TEST TEST DESCRIPTION TEST START DATE TEST END DATE RESPONSIBLE PERSON STATUS COMMENTS
Onboarding Workflow Registration Verify user registration process automation 20-09-2023 21-09-2023 Swetha In Progress Initial test scripts developed.
Onboarding Workflow Document Submission Test document submission automation 22-09-2023 23-09-2023 Swetha Not Started Awaiting completion of registration tests.
Onboarding Workflow Approval Test the automation of approval processes 24-09-2023 25-09-2023 Swetha Not Started Dependent on document submission tests
Dashboard Performance Load Testing Conduct load testing for dashboard responsiveness 26-09-2023 27-09-2023 Swetha Not Started Testing environment setup in progress.
Dashboard Data Accuracy Verify the accuracy of data displayed on dashboards 27-09-2023 28-09-2023 Swetha Not Started Data validation scripts to be developed
Dashboard Real-time Updates Test real-time data updates on dashboards 28-09-2023 29-09-2023 Swetha Not Started Data synchronization mechanism in progress