## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | IAC Community Ambassador Onboarding Process | nity Ambassa
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 07/31/2023
EXPECTED COMPLETION DATE | 08/31/2023
ESTIMATED COST
GOALS,OBJECTIVES,DELIVERABLES
PROJECT OBJECTIVE | The main objective of the project is to create a web application to automate the CA onboarding workflows
BUSINESS CASE | Take forward the social cause of IAC
GOALS/METRICS | To create a web application which help the organisation to track the students efforst for signing up for IAC
EXPECTED DELIVERABLES | App to monitor the onboarding process
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | New Joinee Form,Receiving a welcome email with the UTM link
OUTISDE OF SCOPE | To extract the information from the UTM link
PROJECT RESOURCES AND COST
PROJECT TEAM | Revuru Sree Swetha
SUPPORT RESOURCES | Front-end and Back-end Technologies
SPECIAL NEEDS | N/A
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Harshada Topale
KEY STAKEHOLDERS | Harshada Topale
END CUSTOMER | Cloud Counselage Pvt.Ltd.
EXPECTED BENEFIT | The project helps the IAC to track the performance of Community Ambassadors
PROJECT RISKS,CONSTRAINTS,ASSUMPTIONS
RISKS | Leads to increase of development cost while developing an application
ASSUMPTIONS | Reciveing a correct welcome email after submitting the Joinee form
CONSTRAINTS | Timeline